## Defect Log
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sravanthi | Feb 16 | Difficulty understanding IVR flow design | Sprint 1 | Backend Team | Requirement Issue | Revised IVR flow and simplified call options | Feb 18 | Closed | Initial confusion resolved
2 | Sravanthi | Feb 20 | Incorrect mapping of user inputs in IVR menu | Sprint 1 | Backend Team | Functional Defect | Fixed routing logic for inputs | Feb 22 | Closed | Working properly now
3 | Sravanthi | March 2 | UI not user-friendly for call interaction | Sprint 2 | Frontend Team | UI Defect | Improved layout and button clarity | March 4 | Closed | UI enhanced
4 | Sravanthi | March 5 | Deployment issue (requirements.txt not working properly) | Sprint 2 | DevOps | Configuration Defect | Corrected dependencies and redeployed | March 6 | Closed | Deployment successful
5 | Sravanthi | March 10 | Delay in backend API response | Sprint 2 | Backend Team | Performance Issue | Optimized API calls | March 11 | Closed | Response improved
6 | Sravanthi | March 16 | Issues in AI conversational flow (incorrect responses) | Sprint 3 | AI Team | Functional Defect | Improved prompt handling and logic | March 18 | Closed | Responses improved
7 | Sravanthi | March 20 | Integration issue between IVR and AI module | Sprint 3 | Backend Team | Integration Defect | Fixed API integration | March 21 | Closed | Integration stable
8 | Sravanthi | March 25 | Call flow breaking during real-time testing | Sprint 4 | Backend Team | Critical Bug | Debugged and fixed flow conditions | March 26 | Closed | Stable now
9 | Sravanthi | March 28 | Minor UI glitches in final deployment | Sprint 4 | Frontend Team | UI Defect | Fixed alignment and responsiveness | March 29 | Closed | Final UI polished
10 | Sravanthi | March 30 | Final validation issues before submission | Sprint 4 | Full Team | Testing Issue | Performed final testing and fixes | March 30 | Closed | Project ready