## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | Study the fundamentals and working principles of IVR systems to understand their architecture and flow | MUST HAVE | None | Self | 3- Completed
Sprint 1 | Sprint 1 | US002 | Document the IVR architecture and define the integration approach with conversational services. | MUST HAVE | US001 | Self | 3- Completed
Sprint 2 | Sprint 2 | US003 | Design an API-based middleware layer to enable communication between the IVR backend and conversational components. | MUST HAVE | US002 | Self | 3- Completed
Sprint 2 | Sprint 2 | US004 | Develop REST API connectors to support real-time request and response handling for IVR interactions. | MUST HAVE | US003 | Self | 3- Completed
Sprint 3 | Sprint 3 | US005 | Implement conversational dialogue flows and integrate speech/text interaction handling to support natural language communication with the IVR system. | MUST HAVE | US004 | Self | 3- Completed
Sprint 4 | Sprint 4 | US006 | Conduct system validation by testing conversational and menu-driven IVR functionalities and resolving any issues identified during testing. | MUST HAVE | US005 | Self | 2- In Progress
Sprint 4 | Sprint 4 | US007 | Deploy the integrated IVR system in a local environment and monitor system behavior to ensure stable operation and performance. | MUST HAVE | US006 | Self | 2- In Progress
Mention the US ID(s) on which the user story depends.
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 48 | 3 | 3 | 6 | 6 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
SPRINT 1 BACKLOG
US001 | T1 | Study IVR fundamentals and understand system workflow and architecture | 2026-02-02 | 2026-02-16 | Backend | Others | 3- Completed | 12 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 3
US001 | T2 | Design web simulator architecture for interacting with the IVR backend | 2026-02-17 | 2026-03-02 | Backend | Design | 3- Completed | 12 | Day 3: 3; Day 4: 3; Day 5: 3; Day 6: 3
US001 | T3 | Implement API communication between web simulator and FastAPI backend | 2026-03-03 | 2026-03-16 | Backend | Design | 3- Completed | 12 | Day 6: 3; Day 7: 3; Day 8: 3; Day 9: 3
US001 | T4 | Perform system testing and validate conversational IVR workflow | 2026-03-27 | 2026-03-30 | Frontend | Others | 2- In Progress | 12 | Day 10: 3; Day 11: 3; Day 12: 3; Day 13: 3
Please enter the dates in either of these formats:
9/15/2016 or
15-Sep-2016
Please enter the dates in either of these formats:
9/15/2016 or
15-Sep-2016
This is the total task estimated in hours for all the user stories
Pending effort hours after completion of day 1 work
Pending effort hours after completion of day 2 work
Pending effort hours after completion of day 3 work
Pending effort hours after completion of day 4 work
Pending effort hours after completion of day 5 work
Pending effort hours after completion of day 6 work
Pending effort hours after completion of day 7 work
Pending effort hours after completion of day 8 work
Pending effort hours after completion of day 9 work
Pending effort hours after completion of day 10 work
Pending effort hours after completion of day 11 work
Pending effort hours after completion of day 12 work
Pending effort hours after completion of day 13 work
Pending effort hours after completion of day 14 work
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Difficult to understand IVR call flow and menu navigation logic | Studied Ivr workflow, analyze call flow diagrams and documented the system flow
Sprint 2 | Day 2 | Issues during backend implemented of API endpoints | Debugged FastAPI code and corrected request response handling
Sprint 3 | Day 3 | Fced difficulty handling AI conversation response and intent flow | Improved prompt handling and adjusted conversation logic
Sprint 3 | Day 5 | Ai response not matching Ivr menu options | Updates conversation flow and refined response handling

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-02 | 2026-02-16 | Backend | Start learning IVR sytem architecture and conversational AI flow | Stop unclear requirement discussions | Continue research and documentation | Documented IVR workflow and system modules
2 | 2 | 2026-02-17 | 2026-03-02 | Backend | Start designing and backend API structure | Stop incomplete design drafts | Continue architecture panning | Completed system design and API structure
3 | 3 | 2026-03-03 | 2026-03-16 | Both | Start implementing IVR conversation flow and menu handling | Stop inefficient coding approaches | Continue Backend development | Implemented conversational flow and agent routing
4 | 4 | 2026-03-17 | 2026-03-30 | Both | Start system testing and debugging | Stop unresolved bugs | Continue testing and improvement | Fixed bugs
5
6
7